## OWG - Issues List
2017-02-22
T+ 2
Operations Working Group
Issue list
No. | Issue | Affected Industry Segment (1) | Notes | Issue Status | Estimated work effort
Items completed and awaiting implementation
OWG - 001 | Industry Testing | All | Plan to commence Q1/17 in conjunction with US. | Pending
OWG - 026 | Chi-X Canada ATS and CX2 Canada ATS |  | Minor system/ parameter changes are required. | Pending
OWG - 027 | Instinet Canada Cross Limited ("ICX") |  | Minor system/ parameter changes are required. | Pending
OWG - 028 | CBID / CBID Institutional (Perimeter Markets Inc.) |  | Minor system/ parameter changes are required. | Pending
OWG - 029 | Omega |  | Minor system/ parameter changes are required. | Pending
OWG - 030 | Match Now |  | Minor system/ parameter changes are required. | Pending
OWG - 031 | Liquidnet |  | Minor system/ parameter changes are required. | Pending
OWG - 032 | Candeal |  | Minor system/ parameter changes are required. | Pending
Items completed and CLOSED
OWG - 002 | Trade Funding | S/B/C | FX implications; timing of Retail Cheques and payments | Closed
OWG - 003 | ETF Create/ Redeem | All | Electronic deposits; Corporate action impacts | Closed
OWG - 004 | Derivatives incl. Option Exercise / Assignments | All | need CDCC input/involvement | Closed
OWG - 005 | NI 24-101 | S/B/C | For Legal/Regulatory WG if rule changes required. | Closed
OWG - 006 | International Clients - allocations etc. | All |  | Closed
OWG - 007 | Corporate Actions | S/C/D | Ex-date calculations; Cover/Protect period; Due Bills; DRIP's | Closed
OWG - 008 | Reduced reconciliation/resolution time prior to settlement date | S/C/D | is this inherent in T+2 and an internal procedure issue? | Closed
OWG - 009 | Securities Lending | S/C/D | Loan recalls; repos | Closed
OWG - 010 | Cross-border transactions (US-CDA activities only) | All | Securities need to be moved between CDS and DTCC in order to facilitate settlement. | Closed
OWG - 011 | Capital/collateral implications | All | Client margin implications. | Closed
OWG - 012 | DP Trade Matching | S/D | Lock-in is already set to noon T+1. Change required? | Closed
OWG - 013 | MF/Private and Pool funds | B/S/C | Matching pools with underlying securities; Impact of Fundserve "stamping" of trades | Closed
OWG - 014 | Virtual Matching Utilities (Omgeo/SSandC) | All | Internal systems integration and procedures | Closed
OWG - 015 | Dematerialization (physical) | S/C/D | Not considered material issue as it is not directly related to the success of T+2. | Closed
OWG - 016 | Penalties for fails? | S | Not considered material issue as it is not directly related to the success of T+2. | Closed
OWG - 017 | Deposits/Physical securities (CDS/DTC) | S/C/D | Time/cost of deposit types (Instant/Rush/Regular); Electronic deposits; Treasury directions. Requires STAC involvement | Closed
OWG - 018 | Fixed Income securities | All | Specific to current T+3 investments only. | Closed
OWG - 019 | Buy-Ins | All | Procedural changes if rule changes made. | Closed
OWG - 020 | Global Custody activities | All | This item was removed and the details have been combined with OWG - 006 | Closed
OWG - 021 | Foreign Exchnage |  | Trade and settlements | Closed
OWG - 022 | Seg Funds | All | Item was removed as it is being dealt with as part of the Mutual Funds Sub Working Group | Closed
OWG - 024 | Accured Interest on Trades |  |  | Closed
OWG - 023 | Holiday Processing |  |  | Closed
OWG - 025 | Assets affected by the move to T+2 | All | A list of assets that currently trade T+3 and will move to T+2 should be generated | Closed
OWG - 033 | Restricted Share Transfers (Residency/Hold periods etc) | All | TELUS is an example | Closed

## BLANK TEMPLATE
CCMA T+2
Operations Working Group
Issue: OWG - 0 | ISSUE IDENTIFICATION
Status | OPEN/CLOSED
Description: | To Be Completed
What is the issue: | To Be Completed
Major discussion points: | To Be Completed
Is there more work to be done: | To Be Completed
Completed by the Working Group: | To Be Completed
Date of original posting: | To Be Completed
Revised dates:
Completed date:
Passed to another working Group

## OWG - 001
CCMA T+2
Operations Working Group
Issue: OWG - 001 | Industry Testing
Status | OPEN
Description: | Industry wide testing is a major component of the T+2 project, or will testing be required.
Industry plans will need to be made to determine if the testing will be scripted, or open
to individual testing.
What is the issue: | The process of industry wide testing is very complex.
Will it be tested individually or as an industry
What if someone is not ready to test in Q1 2017
Major discussion points: | CDS and Fundserv to take the lead in developing industry test plans.
High Level test plans released and agreed to in May 2016
Detailed test plans to be completed by mid summer 2016
Tests to run in Q2 and Q3 2017.
Is there more work to be done: | Will testing be mandatory or voluntary.
Will there be a formal sign-off after the completion of testing.
These issues need to be deternined by the end of 2016.
Completed by the Working Group: | To Be Completed
Date of original posting: | 2015-11-24
Revised dates: | 1/20/2016 and 5/11/2016
Completed date:
Passed to another working Group

## OWG - 002
CCMA T+2
Operations Working Group
Issue: OWG - 002 | Trade Funding - Client
Status | CLOSED
Description: | Trade Funding - Client
What is the issue: | Security transactions or cash flows need to be funded on a more timely basis
Major discussion points: | Some clients, normally in the retail space, do not have margined accounts and use security deposits or cheques to fund transactions. (the US estimates upto 20% funded by cheque)
Institutional clients may be accustomed to funding accounts on a T+3 basis - how will they be educated ? (custodian, consultant community)
Is there more work to be done: | This issue has been deemed completed based on the fact that individual firms must undertake internal efforts (process or system changes) in order to effect the required changes.
Completed by the Working Group: | Yes
Date of original posting: | 2015-11-24
Revised dates:
Completed date: | 2016-09-20
Passed to another working Group

## OWG - 003
CCMA T+2
Operations Working Group
Issue: OWG - 003 | ETF - Create/Redeem
Status | CLOSED
Description: | EFT - Create and Redemption process.
What is the issue: | How will the ETF Create and Redeem process be affect by the shortening of the settlement period from T+3 to T+2.
Major discussion points: | The CETFA Operations Committee met and reviewed the ETF- Create/Redeem process. The Committee agreed that at this time there are no known issues related to this process going into a T+2 environment.
The ETF industry currently deals with some products that settle in T+2 and there are no issues. The question relating to volume in a shorter period of time was raised - but again, we do not believe it is an issue. We need however to ensure that it is part of the test.
Is there more work to be done: | CEFTA would like this process to be part of the industry-wide test to ensure that there are no issues
Completed by the Working Group: | Yes
Date of original posting: | 2015-11-24
Revised dates:
Completed date: | 2016-09-20
Passed to another working Group | Was reviewed by the CEFTA Operations committee.

## OWG - 004
CCMA T+2
Operations Working Group
Issue: OWG - 004 | Derrivatives
Status | CLOSED
Description: | Canadian Derivatives Clearing Corporation (CDCC) systems are known as Canadian Derivatives Clearing Service (CDCS). CDCS submits settlement instructions for the delivery of the underlying of an Options position that is Exercises or a Futures position that is Tendered. These settlement instructions are transmitted to CDS' CDSX system for settlement as per the convention of the underlying ISIN.
What is the issue: | Settlements are to move from T+3 to T+2
Major discussion points: | CDCS is fully configurable.
CDCC can and has changed the number of settlement days as BAU.
CDCC completed a UAT cycle in December 2015. No issues were found.
Rule Changes have been identified.
Is there more work to be done:
Rule changes to be filed with CDCC's Regulatory bodies.
Communication to CDCC's Clearing Members. This has been achived via CDCC's Users' Group
meetings and notices.
Completed by the Working Group: | All Rule changes have been filed with the appropriate regulators
All system changes have been programed
Date of original posting: | 2015-12-03
Revised dates: | 1/13/2016, 1/9/2017
Completed date: | 2017-02-22
Passed to another working Group

## OWG - 005
CCMA T+2
Operations Working Group
Issue: OWG - 005 | NI-24-101
Status | CLOSED
Description: | The NI 24-101 is a National Instrument, under the CSA, that describes the timelines
for reporting and confirming trades.
Trades must be reported and confirmed by Noon on T+1, in the current
three day settlement environment.
What is the issue: | The industry needs to consider if this timeline is still appropriate for the new
settlement period of T+2.
Non North American trades must be confirmed by Noon on T+2…is this still appropriate.
Major discussion points: | Confirmation rates are in the low 90s today.
By moving to T+2, the industry still accepts that this timeline is still appropriate.
The 90% matched rate, by member firms was deemed still appropriate.
Non North American client must meet the same timelinbes as domestic clients. That is
Noon on T+1. They will no long be granted an exception when measuring each firm.
This is an educational process to be completed by each member firm.
Is there more work to be done: | Worked completed in May 2016.
Recommendation to T2SC made on May 26, 2016.
Completed by the Working Group:
Date of original posting: | 2015-10-15
Revised dates: | 2016-01-20
Completed date: | 2016-05-11
Passed to another working Group

## OWG - 006
CCMA T+2
Operations Working Group
Issue: OWG - 006 | International Clients - Allocations
Status | CLOSED
Description: | Reduced time for resolving trade allocation issues received from non-North
American clients.
What is the issue: | Where an IM or Broker is trading in Canadian securities on behalf of a client whose custodian is not domiciled in North America. The time to resolve settlement differences is not only inherently reduced but potentially excaerbated by the magnitude of the time difference and any misaligned statutory holidays. Note: custodians normally have local sub or direct custody presence but IM's are normally only allowed to speak with the main contact centre
Due to time zone differences DAP/RAP trade allocations received from non-North American clients for trades that are executed late in the day are normally received and processed on T+1. With the move to T+2 there will be very little time to communicate and resolve trade/allocation issues with non-North American clients prior to value date.
Major discussion points: | Are procedural/system changes required or will education/communication address this issue?
Under NI 24-101 (3.1-2) DAP/RAP trades received/communicated from clients outside the North American region are permitted an additional 24hrs to match (currently noon on T+2). Is this additional 24hrs still an appropriate timeline for these transactions in a T+2 environment?
What is the scope and magnitude of this issue
The committee recommended and agreed that these trades should not have special status. In other words, ALL trades must be confirmed by Noon on T+1 and no longer be allowed an extension to Noon on T+2.
Is there more work to be done: | This item was incorporated into OWG - 005.
The National Instrument 24-101 needs to be updated to reflect this decission
Completed by the Working Group: | To Be Completed
Date of original posting: | 2015-11-24
Revised dates:
Completed date: | 2016-05-11
Passed to another working Group

## OWG - 007
CCMA T+2
Operations Working Group
Issue: OWG - 007 | Corporate Actions
Status | CLOSED
Description: | There are many activities associated with the processing of corporate actions,
such as the Ex-D, RD, PD, DBRD, etc.
What is the issue: | Are there system changes needed to be made in order to meet the shortened timeline.
CDS/FundServ processes CA for the industry. Are their systems hardcoded, or are
processes documented in procedures.
Major discussion points: | CDS/FundServ should identify the proposed changes.
Industry members should determine internal processes/procedures/system that also
need to be modified.
Is there more work to be done: | To Be Completed
Completed by the Working Group: | The working group is confident that all of the Corporate Action items have been
captured and addressed by the various Vendors (eg. Broadridge, IBM, etc) and
Utilities (eg. CDS and Fundserv).
Date of original posting: | 2015-10-15
Revised dates:
Completed date: | 2016-04-13
Passed to another working Group

## OWG - 008 A
CCMA T+2
Operations Working Group
Issue: OWG - 008a | Reduced reconciliation/resolution time for trades
Status | CLOSED
Description: | Current available time for reconciling trades is reduced by 24 hours under T+2
What is the issue: | Do all firms have the ability and resources to ensure timely reconcilliation?
Major discussion points: | Is this an internal procedural consideration to meet accelerated settlement date?
One firm (perhaps more) utilizes a "night shift " of staff to accommodate timely
reconciliation and trade activity balancing process.
Is there more work to be done: | This issue has been deemed completed based on the fact that individual firms must undertake internal efforts (process or system changes) in order to effect the required changes.
Completed by the Working Group: | Yes
Date of original posting: | 2015-11-24
Revised dates:
Completed date: | 2016-09-20
Passed to another working Group

## OWG - 008 B
CCMA T+2
Operations Working Group
Issue: OWG - 008b | Reduced reconciliation/resolution time for trades
Status | CLOSED
Description: | Reduced reconciliation/resolution time prior to settlement date
What is the issue: | BUY SIDE - middle office is the conduit between sell side and custodian when trades are not matching at the depository. Firms monitor email, faxes and web portals to facilitate settlement. Less time to effect this
SELL SIDE
CUSTODIAN
Major discussion points: | BUY SIDE - discuss the improvement to the quality and timelness of custodian reporting
BUY SIDE - examine the workflow concentration and resource implications
BUY SIDE - explore the use of a fails management utility (Bloomberg, Omgeo)
Is there more work to be done: | This issue has been deemed completed based on the fact that individual firms must undertake internal efforts (process or system changes) in order to effect the required changes.
Completed by the Working Group: | YES
Date of original posting: | 2015-11-24
Revised dates:
Completed date: | 2016-09-20
Passed to another working Group

## OWG - 009
CCMA T+2
Operations Working Group
Issue: OWG - 009 | Securities Lending
Status | CLOSED
Description: | Securities on loan need to be recalled for settlement purposes. In a T+2 environment
processes will need to change.
What is the issue: | Do agreements need to be modified.
Do internal processes/procedures/systems need to be modified.
Do utilities/vendors need to make changes to accommodate any foreseen changes.
Major discussion points: | It was determined that lending agreements do not need to be modified.
No changes are required to internal processes or systems.
Is there more work to be done: | None
Completed by the Working Group:
Date of original posting: | 2015-11-01
Revised dates:
Completed date: | 2016-05-11
Passed to another working Group

## OWG - 010
CCMA T+2
Operations Working Group
Issue: OWG - 10 | Cross-Border Transactions
Status | CLOSED
Description: | Northbound/Southbound flips between CDS & DTC
What is the issue: | Will the movements be completed on time in a T+2 environment
Major discussion points: | Since this is performed in realtime on Settlement Date it is not directly related to T+2
Is there more work to be done: | None
Completed by the Working Group: | It was determined that these movements occur in real time when executed, therefore the
current process can exist in a T+2 environment with no implication to trade settlement.
Date of original posting: | 2015-11-24
Revised dates:
Completed date: | 2016-01-13
Passed to another working Group

## OWG - 011
CCMA T+2
Operations Working Group
Issue: OWG - 011 | Capital & Collateral implications
Status | CLOSED
Description: | IIROC firms (and possibly others) are required to put up capital for trades until settled.
What is the issue: | Capital requirements (duration and amount) may change
Major discussion points: | Theoretically, capital usage may decline given the reduction of settlement period to 2 days
This would be a positive impact and basically the prime reason for the move to shortened
settlement cycles - Risk Reduction
May be a side implication from CDS change to earlier "novation" of market trades.
Is there more work to be done: | This issue has been deemed completed based on the fact that individual firms must undertake internal efforts (process or system changes) in order to effect the required changes.
Completed by the Working Group: | Yes
Date of original posting: | 2015-11-24
Revised dates:
Completed date: | 2016-09-20
Passed to another working Group

## OWG - 012
CCMA T+2
Operations Working Group
Issue: OWG - 012 | DP Trade Matching
Status | CLOSED
Description: | Will DP Trade Matching be affected by the transition to T+2.
What is the issue: | To Be Completed
Major discussion points: | This issue is not impacted by the transition to T+2
Is there more work to be done: | No
Completed by the Working Group: | To Be Completed
Date of original posting: | 2015-12-15
Revised dates:
Completed date: | 2015-12-15
Passed to another working Group

## OWG - 013
CCMA T+2
Operations Working Group
Issue: OWG - 013 | Mutual Funds/Private and Pooled funds
Status | CLOSED
Description: | Mutual Funds/Private and Pool funds
What is the issue: | Co-mingled pooled vehicles (open ended mutual funds, pooled funds) have varying settlement cycles driven by the unique needs of each fund. However, a large number currently settle on a T+3 basis primarily so that the cash inflows and outflows can be matched with the cycle of the underlying securities. Should these change to T+2
Major discussion points: | There is no mandatory reason for funds to change their settlement cycle - true or false ?
Firms should examine the requirements of their own vehicles
Therefore, is this primarly a communication and education exercise (both for the CEWG and by firms themselves internally and through to clients)
Is there more work to be done: | This issue was passed onto the Mutual Funds Working Group
Completed by the Working Group: | To Be Completed
Date of original posting: | 2015-11-24
Revised dates:
Completed date: | 2016-05-11
Passed to another working Group

## OWG - 014
CCMA T+2
Operations Working Group
Issue: OWG - 14 | VIRTUAL MATCHING UTILITIES
Status | OPEN
Description: | Utilize Virtual Matching Utilities (VMU) in order to expedite trade
affirmation/allocation/confirmation.
What is the issue: | Successful T+2 Settlement is predicated on timely affirmation,
allocation, and confirmation of trades.
Loss of one day in settlement cycle reduces time to resolve discrepancies
and/or complete account set-up and SSI matches.
Major discussion points: | Assess internal connectivity to ensure highest levels of
straight-through processing (STP)
Assess counterparty utilization and encourage onboarding to
electronic platforms
Is there more work to be done: | Should we have a sub working group identify vendors, present workflows, and recommend actions for all?
Completed by the Working Group: | To Be Completed
Date of original posting: | 2015-12-07
Revised dates:
Completed date:
Passed to another Working Group

## OWG - 015
CCMA T+2
Operations Working Group
Issue: OWG - 015 | Dematerializatoin
Status | CLOSED
Description: | Dematerialization is the elimination of physical securities and replacing them with
electronic or book positions within a Clearing organization.
What is the issue: | There is very little or no time to settle physical securities in physical form.
Major discussion points: | The elimination of physical securities by regulatory means or industry practice (see
Fixed Income market) would benefit the settlement process.
Is there more work to be done: | None
Completed by the Working Group: | Since the act of settlement is outside the scope of the conversion to T+2, this issue
does fit within the mandate of this project.
Date of original posting: | 2015-11-24
Revised dates:
Completed date: | 2016-01-13
Passed to another working Group

## OWG - 016
CCMA T+2
Operations Working Group
Issue: OWG - 016 | Penalties for Fails
Status | CLOSED
Description: | Should penalties be considered for fails in a T+2 environment to encourage faster processing
What is the issue: | Fails should be eliminated to reduce the overall risk of the system.
Major discussion points: | Fails are a post-settlement date process and therefore not required for T+2.
Reducing Fails is always a good thing.
This is not a T+2 issue
Is there more work to be done: | None
Completed by the Working Group: | Since fails occur after settlement has taken place, this issue is outside the scope of the
conversion to T+2, this issue does fit within the mandate of this project.
Date of original posting: | 2015-10-15
Revised dates: | 2015-11-03
Completed date: | 2015-11-25
Passed to another working Group | NA

## OWG - 017
CCMA T+2
Operations Working Group
Issue: OWG - 017 | Deposits/Physical securities (CDS/DTC)
Status | CLOSED
Description: | Physical securities need to be deposited into the clearing corporattion prior to settlement.
What is the issue: | A regular deposit cannot be completed within the timelines needed to complete settlement on T+2.
A Rush depsoit is too expense to utilize on a regular basis.
Major discussion points: | The elimination of physical securities by regulatory means or industry practice (see Fixed Income
market) would benefit the settlement process.
Is there more work to be done: | None
Completed by the Working Group: | Since the act of settlement is outside the scope of the conversion to T+2, this issue does fit
within the mandate of this project.
Date of original posting: | 2015-11-24
Revised dates:
Completed date: | 2016-01-13
Passed to another working Group

## OWG - 018
CCMA T+2
Operations Working Group
Issue: OWG - 018 | Fixed Income Issues
Status | CLOSED
Description: | Issues specific to Fixed Income in a T+2 environment that need to modified.
What is the issue: | System, rules, process, procedural changes, etc need to be examined prior to the implmentation of T+2
Major discussion points: | It was determnined that issues relative to Fixed Income will be the same at Equities.
When addressing Equities, we will incorporate any consuderations needed for Fixed Income
Is there more work to be done: | None
Completed by the Working Group: | It was determined that this issue can be closed as the issues will be the same as equities.
Date of original posting: | 2015-11-24
Revised dates:
Completed date: | 2015-11-27
Passed to another working Group

## OWG - 019
CCMA T+2
Operations Working Group
Issue: OWG - 019 |  | Buy-Ins
Status |  | CLOSED
Description: |  | Buy In processing impact of moving from T+3 to T+2 on CDS rules, systems, internal, external procedures.
What is the issue: | 1) | The execution dates for intent to buy in is not affected by T+2. The execution date is: either notice day + 2
if notice of intent is served between 7:00 am and 5:00 pm ET or notice date + 3 if notice is served
between 5:00 pm and 7:30 pm ET. There is no impact moving to T+2 on CDS systems, internal and external procedures.
| 2) | The execution of buy-ins can be done as a cash trade or regular trade. A cash trade settles on T+1. Although regular trade settlement will move from T+3 to T+2, there will be no impact on CDS systems
and external procedures as the value date for settlement is entered when creating the trade. CDS
internal procedures to be updated.
Major discussion points:
Is there more work to be done: |  | Suggest this issue can be closed as the only impact is on CDS internal procedures.
Completed by the Working Group: |  | Closed
Date of original posting: |  | 2015-11-24
Revised dates:
Completed date: |  | 2016-05-11
Passed to another working Group

## OWG - 020
CCMA T+2
Operations Working Group
Issue: OWG - 020 | Global Custody Activities
Status | CLOSED
Description: | Global Custodian
What is the issue: | Where an IM or Broker is trading in Canadian securities on behalf of a client whose custodian is not domiciled in North America. The time to resolve settlement differences is not only inherently reduced but potentially excaerbated by the magnitude of the time difference and any misaligned statutory holidays. Note: custodians normally have local sub or direct custody presence but IM's are normally only allowed to speak with the main contact centre
Major discussion points: | What is the scope and magnitude of this issue
How are firms dealing with this now (in essence a version of this problem already exists when trading European (or any T+2 market) for clients with north american custodians
Is a true follow the sun service method required
Is there more work to be done: | To Be Completed
Completed by the Working Group: | This item is being closed and will be dealt with as part of OWG - 006.
Date of original posting: | 2015-12-15
Revised dates:
Completed date: | 2015-12-15
Passed to another working Group

## OWG - 021
CCMA T+2
Operations Working Group
Issue: OWG - 021 | Foreign Exchange
Status | CLOSED
Description: | Standard Foreign Exhange settlement cycle no longer has a one day buffer
What is the issue: | BUY SIDE - Spot Forex deals typically settle on a T+2 basis (for 3rd party transactions). This normally affords a manager time to aggregate the currency requirements as late as the morning following trade date and still meet the funding requirement
Major discussion points: | INDUSTRY - discuss whether it is appropriate to modify the standard settlement period.
Some custodian cut-offs may curently be incompatible.
BUY SIDE - Managers are coping with the current cycle in Europe but is this the best model ?
Is there more work to be done: | This issue has been deemed completed based on the fact that individual firms must undertake internal efforts (process or system changes) in order to effect the required changes.
Completed by the Working Group: | Yes
Date of original posting: | 2015-11-24
Revised dates:
Completed date: | 2016-09-20
Passed to another working Group

## OWG - 022
CCMA T+2
Operations Working Group
Issue: OWG - 022 | Seg Funds
Status | CLOSED
Description: | Insurance Seg Funds
What is the issue: | Will Seg Funds be impacted by the transition to T+2
Major discussion points: | To Be Completed
Is there more work to be done: | To Be Completed
Completed by the Working Group: | This issue will be dealt with as part of the Mutual Funds Working Group (MFWG).
Date of original posting: | 2015-10-15
Revised dates:
Completed date: | 2015-12-15
Passed to another working Group

## OWG - 023
CCMA T+2
Operations Working Group
Issue: OWG - 023 | Holiday Processing
Status | CLOSED
Description: | What system or operational processes need to change to accommodate the various
regional statutory holidays in both Canada and the US.
What is the issue: | 1) With a shortened settlement period, combined with a single center holiday (e.g.. St Jean
Batiste in June for Quebec) how will firms complete the necessary tasks to ensure that
trades are ready for settlement.? In Quebec, a trade on the TSX on June 23rd, will settle
on June 25th. A Montreal based firm will contract the trade on the 23rd, but due to the
holiday on the 24th, will not see the trade until the 25th or T+2. This means if there are problems
with the transaction there is no time to make corrections prior to settlement date.
2) CDS has now implemented early novation such that trades will now be marked to market on the evening of T in the T+2 environment. Accordingly, CDS participants will not have an opportunity to correct trades prior to the execution of the mark to market calculation. There is, therefore, the potential that a participant or participants could be materially impacted in the event that a single large transaction, or a large number of transactions, is or are reported to CDS, resulting in the calculation of an improper collateral amount required by the CDS risk management system.
Major discussion points: | 1) Firms will need to review staffing levels to ensure that they have the appropriate number of staff to manage all of their operational processes in a T+2 environment. This includes, considering shift work, split work streams, additional automation, etc.
1) CDS and the exchanges have implemented an enhanced communication process to manage the expected Settlement dates during all holidays throughout the year.
2) CDS has indicated that, in the event that reporting of incorrect trades materially impact the collateral determined by the CDS risk management systems, CDS will work with individual firms (or the entire community) to mitigate any adverse impact on the participant(s). Mitigation will include, but is not limited to, the reversal of collateral calls for a single security, an entire trade file, or an incorrect price. CDS will communicate the correction process to participants affected by the error.
Is there more work to be done: | None
Completed by the Working Group: | Closed
Date of original posting: | 2016-01-15
Revised dates: | 2016-11-22
Completed date: | 2016-01-17
Passed to another working Group

## OWG - 024
CCMA T+2
Operations Working Group
Issue: OWG - 024 | Accured Interest on Trades
Status | OPEN
Description: | This is related to the way that interest is apportioned to buyers and sellers of bonds between coupon payments and how this is reflected in fund valuations.
What is the issue: | Will valuation systems be affected by the transition to T+2
Major discussion points: | When you purchase a bond, you pay the seller the price of the bond plus an amount equal to the proportionate earned interest since the last coupon date and calculated out to settlement date. When this transaction is recorded in a valuation system the new bonds are added to the portfolio and the price dictates the economic value added to the total assets. At this stage no interest receivable is accrued because the portfolio does not start earning this until the day after settlement date( remember the seller was paid this amount) . However, on trade date (and every day till settlement) the valuation will record a liability equal to the cash amount it owes to the seller – i.e. the number of bonds x price plus accrued (to a three day settlement). Left alone this will create a temporary impairment of the total asset value because the liability exceeds the asset by the amount of the interest paid to the seller. Normal practice is to offset the whole paid interest amount for the duration of settlement with an entry typically called trade interest – this essentially replaces what would have been a daily accrual but crucially is briefly overstating the amount because calculated forward to settlement. The opposite is true when you sell a bond; the portfolio would receive a payment equal to interest 3 days beyond the trade date and offset this with ‘trade interest’
In its simplest form the proportionate amount that is offset through the settlement period will need to be calculated on 2 extra days instead of 3. Most valuation systems will do this automatically based on the absolute value of interest attached to the payment (in other words it ignores the basis of calculation).
Is there more work to be done: | Fund managers should ensure that their valuation systems have been properly modified to take into accoun the transition to T+2.
Completed by the Working Group:
Date of original posting: | 2016-01-15
Revised dates: | 2016-11-22
Completed date:
Passed to another working Group

## OWG - 025
CCMA T+2
Operations Working Group
Issue: OWG - 025 | Assets affected by the move to T+2
Status | CLOSED
Description: | A list of assets or security types that will be effectd by the move to T+2 should be
generated to assist the industry.
What is the issue: | In order for the industry to focus on the changes required to convert to T+2, a complete
asset list would help.
Major discussion points: | Identify all asset classes known within the industry.
Confirm which asset classes are affected, and which ones are not affected by the move to T+2
Compare with the US list of assets.
Is there more work to be done: | Confirm the current asset list for completeness and accuracy.
Completed by the Working Group: | The Final List was published in July 2016. An updated list was published in December 2016.
The US Asset List has been published.
A comparision document has been completed.
Date of original posting: | 2016-01-14
Revised dates: | 4/13/2016 6/7/2016 12/016
Completed date: | 2016-01-17
Passed to another working Group

## OWG - 026
T+2
Operations Working Group
Issue: OWG - 026 | Chi-X Canada ATS and CX2 Canada ATS
Status | OPEN - Recieved from the LRWG-027 February 17, 2016
Description: | ATS subscriber agreements may specify settlement timeframes.
What is the issue: | Do the ATS's require trades to be settled on a T+3 basis?
Major discussion points: | Chi-X Canada ATS and CX2 Canada ATS have publicly available subscriber agreements
(no amendments required).
CX2 notice "Notice of Initial Operations Report and Request for Feedback" (on OSC website): “All trades matched on CX2 will settle by default on a T+3 basis. In the case of a special direction for clearing and settlement, CX2 will make the appropriate adjustments to indicate the special clearing to CDS.” Nov. 8, 2012: http://www.osc.gov.on.ca/en/Marketplaces_ats_20121108_cx2_rfc-cx2-canada-ats.htm
Systems or Parameter changes: | Yes.
Internal Procedures or Process Amendments: | Subscriber manual will require NI 21-101F2 filing.
Is there more work to be done: | As above.
Completed by the Working Group: | To Be Completed
Date of original posting: | 2015-12-03
Revised dates: | 2016-01-27
Completed date:
Passed to another working Group | Rec'd from LRWG - 207

## OWG - 027
T+2
Operations Working Group
Issue: OWG - 027 | Instinet Canada Cross Limited ("ICX")
Status | OPEN - Received from LRWG-056 on February 17, 2016
Description: | ATS subscriber agreements may specify settlement timeframes.
What is the issue: | Does Instinet specify a T+3 settlement period in its subscriber agreement (or other documentation)?
Major discussion points: | ICX has confirmed its subscriber agreement does not specify a settlement timeline.
Systems or Parameter changes: | Yes. Systems and parameter changes are required.
Internal Procedures or Process Amendments: | NI 21-101F2 filings are required.
Is there more work to be done: | NI 21-101F2 filings are required.
Completed by the Working Group: | Obtained confirmation from ICX.
Date of original posting: | 2015-12-03
Revised dates: | 2016-01-28
Completed date:
Passed to another working Group | OWG

## OWG - 028
T+2
Operations Working Group
Issue: OWG - 028 | CBID / CBID Institutional (Perimeter Markets Inc.)
Status | OPEN - Received from LRWG-060 on February 17, 2016
Description: | ATS subscriber agreements may specify settlement timeframes.
What is the issue: | Does CBID specify a T+3 settlement period in its subscriber agreement (or other documentation)?
Major discussion points: | Operates fixed income and futures marketplaces. CBID's subscriber agreement is not publicly available. Changes not required for the subscriber agreement for CBID or CBID Institutional.
Systems or Parameter changes: | Minor system and parameter changes are required.
Internal Procedures or Process Amendments: | NI 21-101F2 filings not required.
Is there more work to be done: | No.
Completed by the Working Group: | Confirmation from Perimeter.
Date of original posting: | 2015-12-03
Revised dates: | 2016-02-05
Completed date:
Passed to another working Group | OWG

## OWG - 029
T+2
Operations Working Group
Issue: OWG - 029 | Omega Securities Inc. (Omega ATS & Lynx ATS)
Status | OPEN - Received from LRWG-053 on March 23, 2016
Description: | ATS subscriber agreements may specify settlement timeframes.
What is the issue: | Do the ATS's require trades to be settled on a T+3 basis?
Major discussion points: | Omega ATS & Lynx ATS have publicly available subscriber agreements (no amendments required).
OSI client documentation refers to compliance with CDS's settlement process (setttlement period is not specifically stated in OSI documents).
OSI will inform its clients of the shift to T+2 at an appropriate future date.
Systems or Parameter changes: | System is parameter driven and can be changed to T+2 when required.
Internal Procedures or Process Amendments: | None required. No NI 21-101F2 filing amendments required.
Is there more work to be done: | Not from a legal or regulatory perspective.
Completed by the Working Group: | Obtained confirmation from OSI.
Date of original posting: | 2015-12-03
Revised dates: | 2016-01-28
Completed date: | 2016-01-14
Passed from another working Group | LRWG - 053

## OWG - 030
T+2
Operations Working Group
Issue: OWG - 030 | MATCH Now (TriAct Canada Marketplace LP)
Status | OPEN - Received from LRWG-058 on March 23, 2016
Description: | ATS subscriber agreements may specify settlement timeframes.
What is the issue: | TriActs's subscriber agreement is not publicly available
Major discussion points: | Changes to subscriber agreement may be made to inform customers of T+2 (current form of agremeent does not hard code T+3); there will be systems/parameter changes and NI 21-101F2 filings.
Systems or Parameter changes: | Yes.
Internal Procedures or Process Amendments: | Yes.
Is there more work to be done: | To be determined.
Completed by the Working Group: | Request for information sent to TriAct.
Date of original posting: | 2015-12-03
Revised dates: | 2016-02-23
Completed date:
Passed from another working Group | LRWG - 058

## OWG - 031
T+2
Operations Working Group
Issue: OWG - 031 | Liquidnet Canada Inc.
Status | OPEN - Received from LRWG-057 on March 23, 2016
Description: | ATS subscriber agreements may specify settlement timeframes.
What is the issue: | Does Liquidnet Canada ATS specify a T+3 settlement period in its subscriber agreement (or other documentation)? Are amendments required re: T+2?
Major discussion points: | Systems changes to be tracked by OWG.
Systems or Parameter changes: | ATS subscriber agreement - Liquidnet has confirmed no changes are required.
Internal Procedures or Process Amendments: | There are no NI 21-101F2 filings to be made by Liquidnet?
Is there more work to be done: | To be determined.
Completed by the Working Group: | Inquiries made to Liquidnet.
Date of original posting: | 2015-12-03
Revised dates: | 2016-03-04
Completed date:
Passed from another working Group | LRWG - 057

## OWG - 032
T+2
Operations Working Group
Issue: OWG - 032 | CanDeal
Status | Passed from LRWG - OPEN
Description: | ATS subscriber agreements may specify settlement timeframes.
What is the issue: | Does Candeal specify a T+3 settlement period in its subscriber agreement (or other documentation)?
Major discussion points: | Candeal's subscriber agreement is not publicly available.
Systems or Parameter changes: | Systems changes to be tracked by OWG.
Internal Procedures or Process Amendments: | ATS subscriber agreement - Candeal has confirmed no changes are required.
Candeal has confirmed no 21-101F2 filings required.
Is there more work to be done:
Completed by the Working Group: | LRWG Comp work on agreements
Date of original posting: | 2015-12-03
Revised dates: | 2016-05-18
Completed date:
Passed to another working Group | LRWG - 054

## OWG - 033
CCMA T+2
Operations Working Group
Issue: OWG - 033 | Restricted Share Transfers (Residency/Hold periods etc)
Status | CLOSED
Description: | Using Telus as an example. In a T+3 environment, the conversion from non-resident to resident shares takes 48 hours
to complete. In T+3, if the request is submitted on the morning of T+1, the conversion gets completed on T+3.
What is the issue: | In a T+2 environment, the trade cannot be completed prior to Settlement Date.
Major discussion points: | The committee discussed options to address this issue, including using the same day ‘rush’ service provided by
the TA, but that this was very expensive.
The committee also discussed the option of enabling internal procedures to not executing a trade of non-resident shares
until after the conversion to resident shares was completed. However, this was deemed inefficient by some members.
Is there more work to be done: | CDS met with Computershare on a numbe of occasions. TELUS feels that the current process is good and does not need changing.
The OWG agreed that this issue will not prevent the conversion to T+2
This issue will be referred to the CDS SDRC - Equity and Debt Committee
Completed by the Working Group: | To Be Completed
Date of original posting: | 2016-05-11
Revised dates:
Completed date: | 2017-02-22
Passed to another working Group