## MFWG - Issues List
T+ 1
Mutual Funds Working Group
Issue list
No. | Issue | Notes | Issue Status
Open Items
Action Required by Fundserv
MFWG - 001 | Will some funds not move to T+1 because of liquidity concerns? | If a fund is in net redemptions for the previous day, fund managers won't know until the morning of T+1. This leaves insufficient time to redeem securities if a fund has insufficient cash. Survey results showed 25 of 26 respondents supported the move to T+1. Members with OM products or funds that already have longer settlement cycles due to either highly illiquid investments or in foreign markets, would not move to T+1, just like they did not move to T+2. Further to this, we await the IFIC Board response letter to the CSA. | Open
MFWG - 002 | Will ICT's continue as is? | Today In Cash Transfers redemptions settle on T+2 and buys settle on T+1, will this continue? It was agreed that the ICT is the most elegant solution for this type of transaction for both advisors and fund companies. One of the larger dealer service providers programmed this a year ago. Fundserv promoted this at the Fundserv MFDA Advisory Council and gave members a takeaway to explain why they aren't using it. | Closed | No
MFWG - 003 | When will changes be made to the Fundserv Standards? | There are changes to the Standards that are required to be made. When will that be? | Open
MFWG - 004 | Will the settlement cycle of direct redemptions and switches change? | A proposal under DOT 100 was made to the T+1 Working Group to have direct redemptions and switches, and wire order switches, settle on the night of T+1. | Open
MFWG - 005 | How will dealers be able to obtain investor money in time to settle purchases? | Dealers that operate a trust account will be challenged to ensure they have investor money in time to settle purchases by T+1. For client name purchases where the dealer doesn't operate a trust account, how will a client written cheque, payble to the fund company, be delivered by T+1? 9 out of 13 dealers responded that with N$M settlement and EFT they had the tools to settle via T+1. Comments were that T+2 was already a problem for one dealer and another said they need to put in place process to ensure deposits are created at the time of purchase placement. | Closed | No
MFWG - 006 | How will international funds be able to fund redemptions on T+1? | Members shared that for funds invested in securities from international exchanges, there may be difficulty settling by T+1. Survey results showed 25 of 26 respondents supported the move to T+1, so this is not perceived to be an issue. Further to this, we await the IFIC Board response letter to the CSA. | Open
MFWG - 007 | How will Fundserv and dealers be informed which funds are moving to T+1? | How will a fund company notify Fundserv and dealers that they Settlement Period of a fund has changed to T+1? | Open
MFWG - 008 | How will cancellations or modifications of orders be processed? | Currently, after 4pm, pending wire orders cannot be cancelled or modified, but they are subject to dilutions as they would use the next business day's price to trade out. Cancels can be done on Settlement Date, come V33. Modifications will not be permitted. | Closed | V33
MFWG - 009 | How will pre-funding activities be completed on time? | Some fund companies begin their pre-funding calculations during the morning of T+1 to provide reports to fund manager. How will they do this when they have to settle on T+1? Fund companies can run inter-day queries for fund managers to act on before the 4pm cut-off. No other suggestions were made nor any further concerns. | Closed | No
Potential Items for Issue Log:
Action Required by Fundserv
1 | 5% borrow rule? | Should we propose to the regulators to exclude redemptions from the current 5% borrow rule? Per Ali Jaffer of Sun Life. The group agreed not to move forward with this because redemptions are what the 5% borrow rule is all about. | Closed | No
2 | Will we need to host Mock Testing cycles? | In terms of industry testing, will we be having mock environments like with T+2 – we had schedules with fake holidays to simulate go live weekend (we don’t know when this is happening yet, so can't say yet). Members could take part in 1 of 3 mock cycles. Also, testing was not mandatory and there was no attestation like we had with the flat file to XML (V24) | Closed | Yes
3 | Unrelated FD files on implementation weekend allowed? | In the move to T+2 in 2017, there was concern that manufacturers would send Fund Setup Files (FD) on the implementation weekend that had nothing to do with T+2. We are not sure why dealers would have this concern. In 2017 we recommended that manufacturers not do so. Should we do so again? We agreed that like in 2017 Fundserv will instruct fund companies to not send FD files unrelated to T+1. | Closed | Yes
4 | Reversals on Settlement date for T+1 funds, will this be an issue? | Reversals on Settlement date for T+1 funds, will this be an issue? This is being dealt with inFundserv's Industry SME Group (ISG). This will be part of V33. | Closed | V33
5 | List of funds by Settlement Date | In the transistion to T+2 we were asked to provide a CSV list of funds with the Settlement Period, because there were a significant number of dealers that did not import the FD file. Member feedback was yes, they require a CSV file. | Closed | Yes
6 | Overdraft Rules | Will/can NI 81-102 overdraft rules be changed to allow more flexibility for funding? IFIC is reviewing, closing on our Action Log | Closed | No
7 | Current T+1 funds | Any changes to the T+1 current funds? The working group could not come up with any reasons why a T+1 would change. | Closed | No
8 | Custom valuation funds | Any impacts/changes to custom valuations? No changes, as they aren't governed by NI 81-102. | Closed | No
9 | Error Corrections | How will corrections work to ensure that corrections don’t happen while money is in transit? With V33, dealers will be able to place reversal Error Correction transactions and fund companies will have to use that day's NAV to calculate potential dilutions. | Closed | V33
10 | Fund initiated trades | How will fund initiated transactions be impacted: Including PAC/SWP, RIF Payments, IDs. The will remain settling on T. | Closed | No
11 | Availability of contracts in FS file from Fundserv | When will Fundserv files be due to allow time for settlement processes? No changes are expected as no member has shared a business problem that needs to be solved. | Closed | No
12 | Which funds will move? | With the switch from T+3 to T+2 some funds have remained at T+3, what criteria is being proposed to allow some funds currently at T+2 to remain at T+2? The draft CSA mandate is for all funds governed by NI 81-102 must make the move to T+1. Others can decide for themselves. We know that some OM funds have shared they will not move to T+1. We have asked this working group several times if they know of any other products aren't going to move and have not received a response. | Closed | No
Closed Items: None

## MFWG - 001
CCMA T+1
Mutual Funds Working Group
Issue: MFWG - 001 | The ability to fund redemptions and switches by T+1
Status: OPEN
DATE OPENED: Jan. 27, 2022
Description: | If a fund is in net redemptions for the previous day, fund managers aren't notified until the morning of T+1. This could be as a result of redemptions, or switch-outs to other fund codes. If there isn't enough cash in a fund, with T+2, fund managers have the option of leveraging shortened settlement cycle of securities. With T+1, this leaves insufficient time to redeem securities to settle on the same day, as it would likely be difficult to place a redemption order for a stock on T+1 and have it settle in time to meet the 1pm Fundserv cut-off on the same day.
Potential Solutions | There are several options: 1. Change the cut-off to 3pm for redemptions to give fund managers time to sell securities. This may not be appealing for advisors, as other securities likely will retain 4pm cut-off. 2. Stop cancels at 3pm. 3. Keep funds as T+2 settlement for buys and sells. 4. Settle buys on T+1 and sells on T+2. 5. Hold more cash in funds. 6. Run reports throughout the day for portfolio managers so they can sell securities before the 4pm cut-off.
Next Steps | A vote will be issued in the month of April for discussion in the April meeting.

## MFWG - 002
CCMA T+2
Mutual Funds Working Group
Issue: MFWG - 002 | Will ICT's continue as is?
Status: OPEN
DATE OPENED: Jan. 27, 2022
Description: | In Cash Transfers (ICT) are for client name accounts where an investor is selling a fund from Fund Company A to buy a fund at Fund Company B. Instead of sending a redemption and waiting for the proceeds to be able to place the buy, a dealer can do it all in one step by placing and ICT. For ICT's, on T+1 Fundserv receives the contract for the redemption, which settles on T+2. On T+1, Fundserv creates a buy order for Fund Company B, and the order has a T+1 settlement. In that way, the sell and buy settle on the same day, which is T+2. Will this continue when the industry moves to T+1?
Potential Solutions | 1. Leave as is. Continue to have the redemption side of an ICT will settle on T+2 and the buy will settle on T+1. 2. Eliminate ICT's from the Standards.
Next Steps | A vote will be issued in the month of April for discussion in the April meeting.

## MFWG - 003
CCMA T+2
Mutual Funds Working Group
Issue: MFWG - 003 | When will changes be made to the Fundserv Standards?
Status: OPEN
DATE OPENED: Jan. 27, 2022
Description: | With existing functionality, a fund company could change the settlement date of a fund to T+1 via the Fund Setup file and this would be stored by Fundserv and transmitted to all dealers. But there many other updates to the Standards that need to be updated as a result of this change. We need to include them in a release.
Potential Solutions | 1. Include in the June 2023 V33 Release. The cut-off for finalizing requirements is mid-May 2022. 2. Include in the June 2024 V34 Releasse. The cut-off for finalizing requirements is mid-May 2023. This would likely be too late, depending on the U.S. date. 3. Publish a Point Release in October 2023. This would give us much more time to prepare and is Fundserv's recommendation.
Next Steps | Thus far, members have been supportive of the Fundserv proposed schedule if the date is Q1 2024, like the SEC has proposed. The U.S. industry is expected to respond to the SEC that they prefer the Memorial Day weekend, which is at the end of May 204. The CCMA is likely going to respond saying they prefer a date no later than September 30 2024, with the Labour Day weekend being ideal.

## MFWG - 004
CCMA T+2
Mutual Funds Working Group
Issue: MFWG - 004 | Will the settlement cycle of direct redemptions and switches change?
Status: OPEN
DATE OPENED: Jan. 27, 2022
Description: | Despite what the Settlement Period is for a fund bought or sold through Fundserv over the years, for directs, meaning orders delivered by mail, courier or fax, redemptions and switches are processed on T. The next morning fund managers find that money has left their funds and are potentially in overdraft if they didn't carry sufficient cash. This liquidity problem will be further heightened with the transistion to T+1 because it will be difficult for fund managers to settle wire orders on T+1 as well.
Potential Solutions | The Fundserv Funnel has DOT 100 - Settlement Cycles of Direct vs Wire Order Redemptions. The potential solution is to harmonize the settlement of direct and wire order sells and switches. In June 2021 the Fundserv Standards Steering Committee decided not to include it in the V32 Release scope for May 2022. They were more in favour of implementing this at the same time as the transistion to T+1, to minimize effort.
Next Steps | A vote will be issued in the month of April for discussion in the April meeting.
Passed to another working Group

## MFWG - 005
CCMA T+2
Mutual Funds Working Group
Issue: MFWG - 005 | How will dealers obtain investor money in time to settle purchases?
Status: OPEN
DATE OPENED: Jan. 27, 2022
Description: | Dealers that operate a trust account will be challenged to ensure they have investor money in time to settle purchases by T+1, especially if they do not live in the same geographic area.
Potential Solutions | 1. Use N$M or EFT to settle purchases. Send investor or dealer cheques by courier, will be very risky. Furthermore, part of the scope of the Fundserv Working Group called Removing Cheques as a Settlement Method includes prohibiting of issuance of cheques to another Fundserv member as they can leverage N$M, A$M and EFT. 2. Require money to be deposited to the dealers trust account by.
Next Steps | Once we have flushed out all of the options, we can determine a plan to share this with dealers.

## MFWG - 006
CCMA T+2
Mutual Funds Working Group
Issue: MFWG - 006 | How will international funds be able to fund redemptions on T+1?
Status: OPEN
DATE OPENED: Jan. 27, 2022
Description: | Members shared that for funds invested in securities from international exchanges, there may be difficulty settling by T+1.
Potential Solutions | In MFWG - 001, the following three tactics are being considered. Perhaps they apply here as well: 1. Change the cut-off to 3pm for redemptions to give fund managers time to sell securities. This may not be appealing for advisors, as other securities likely will retain 4pm cut-off. 2. Stop cancels at 3pm. 3. Keep funds as T+2 settlement for buys and sells. 4. Settle buys on T+1 and sells on T+2. 5. Hold more cash in funds.
Next Steps | Members will be asked to vote if they think international funds governed by NI 81-102 be able to fund redemptions on T+1 and hence me able to make the transition to T+1?
Completed date:
Passed to another working Group

## MFWG - 007
CCMA T+2
Mutual Funds Working Group
Issue: MFWG - 007 | How will Fundserv and dealers be informed which funds are moving to T+1?
Status: OPEN
DATE OPENED: Jan. 27, 2022
Description: | The Settlement Period of buys and sells is determined by fund companies and is sent to Fundserv via the Fund Setup File (FD). Fundserv informs dealer systems of the Settlement Period field, via the Fund Setup File, to launch, modify, or close a fund. Fundserv uses this field to calculate and assign the trade date and settlement date for all transactions. How will the change from T+2 to T+1 be executed via the FD file?
Potential Solutions | With the transistion to T+2, fund companies were all given a due date in which they must have sent an Fund Setup File with the new Settlement Period, using an effective date that is the weekend of the transistion. Fundserv recommends that this approach be used once again as it was effective in 2017's move to T+2.
Next Steps | A survey will be issued to working group members in early April to ask should Fundserv change all funds to T+1 or follow the same path as in 2017 when we moved to T+2, where fund companies were required to send A Fund set up file (FD or MD) Fundserv was reluctant to move all funds and find that fund companies failed settlement when we move them.

## MFWG - 008
CCMA T+2
Mutual Funds Working Group
Issue: MFWG - 008 | How will cancellations or modifications of orders be processed?
Status: OPEN
DATE OPENED: Jan. 27, 2022
Description: | Currently, after 4pm, pending wire orders can be cancelled or modified. They are subject to dilutions as they would use the next business day's price to trade out. With the move to T+1, after 4pm on Trade Date would actually be considered Settlement Date. Unfortunately, there aren't clear Standards on how a fund company should process cancels or modificiations on Settlement Date. Some fund companies reject them, some accept, but use the price of T+3 to calculate dilutions and some use the Settlement Date price, which is what dealers want.
Potential Solutions | DOT 80 - Reversals on Settlement Date, was created for this issue. It is being actively worked on by Fundserv's Industry SME Group (ISG). It is hoped it will be included in V33 scope for June 2023.
Next Steps | Members to confirm if DOT 80 addresses all of their concerns. Dot 80 will enable members to cancel trades on settlement date.

## MFWG - 009
CCMA T+2
Mutual Funds Working Group
Issue: MFWG - 009
Status: OPEN
DATE OPENED: Feb 24, 2022
Description: | How will pre-funding activities be completed on time? Currently, after 4pm, pending wire orders can be cancelled or modified, but they are subject to dilutions as they would use the next business day's price to trade out.
Potential Solutions | Fund managers can run interday reports and provide them to fund managers.
Next Steps | Further feedback is required from members.